## TestCase
Product Name |  | pchousebd | TC Start Date | 15/12/2024 | TC Execution Start Date | 15/12/24 |  |  |  |  | TEST CASE
Module Name |  | Registration,Login,Logout,Forget Password,Search,Header,Footer | TC End Date | 20/12/2024 | TC Execution End Date | 28/1/24 |  |  |  |  | PASS | 51
Epic |  |  | Test Case Developed By | Syed Muztaba Ali | Browser (tested) | Yes |  |  |  |  | FAIL | 25
Developer Name (TL) |  |  | Test Case Reviewed By | Ehsanul Alam Sabbir | Performance (tested) | N/A |  |  |  |  | NO RUN | 0
Test Executed by | [10 empty] | BLOCKED | 0
[11 empty] | TOTAL | 76
Test Case ID | Module | Type of Testing | Features | Test Cases | Exepected Result | Actual Result | Test Data | Reproducing Steps | Bugs Screen Shot | Dev Comments | Final Status | Remarks
TC_01 | compatibility | Browser Compatibility Testing |  | Checking by running the URL site in different browsers. | Should be run in different browsers. | Found as per expectation. | Browsers-Chrome, Internet Explorer, Mozilla Firefox, Microsoft Edge, Opera Mini. | 1. Go to different browsers. 2. Search 'pchousebd'. 3. Go to the website. |  |  | Passed
TC_02 | Registration |  |  | Verify by clicking on the submit button for blank input. | Should give warning message | Found as per expectation. | none | 1. Go to https://www.pchouse.com.bd/index.php?route=account/register |  |  | Passed
TC_03 |  |  |  | Verify by giving only first or last name | Should give warning message | Found as per expectation. | Muztaba, Utshob | 1. Go to https://www.pchouse.com.bd/index.php?route=account/register |  |  | Passed
TC_04 |  |  |  | Verify by giving comma as first name | Should give warning message | Accepting the given data. | , | 1. Go to https://www.pchouse.com.bd/index.php?route=account/register | https://drive.google.com/file/d/1K1SAkB7ziTX7H5hHt87Q6ih40d52mKh2/view?usp=drive_link |  | Failed
TC_05 |  |  |  | Verify by giving comma as last name | Should give warning message | Accepting the given data. | , | 1. Go to https://www.pchouse.com.bd/index.php?route=account/register | https://drive.google.com/file/d/1lHNvVNsVUEgvruQ0ddBYkSuiZBEOp1x-/view?usp=drive_link |  | Failed
TC_06 |  |  |  | Verify by giving comma as first name and last name | Should give warning message | Accepting the given data. | , | 1. Go to https://www.pchouse.com.bd/index.php?route=account/register | https://drive.google.com/file/d/1N6W-RKgIP8X-itFSLdmY5Pgsu0JzPg8n/view?usp=drive_link |  | Failed
TC_07 |  |  |  | Verify by giving special characters as first name and last name and both | Should give warning message | Accepting the given data. | @$# #%% | 1. Go to https://www.pchouse.com.bd/index.php?route=account/register | https://drive.google.com/file/d/1LLX9uZCfaUyGAaYktf4-N_zIJdoFANQt/view?usp=drive_link |  | Failed
TC_08 |  |  |  | Verify by giving multiple account using same mobile number | Should give warning message | Accepting the given data. | none | 1. Go to https://www.pchouse.com.bd/index.php?route=account/register | https://drive.google.com/file/d/1sr7O0phDD4_25r0yQ4U0mj-SnMIKId84/view?usp=drive_link |  | Failed
TC_09 |  |  |  | Verify by giving multiple account using same email | Should give warning message | Found as per expectation. | none | 1. Go to https://www.pchouse.com.bd/index.php?route=account/register |  |  | Passed
TC_10 |  |  |  | verify by giving characters or special characters in Telephone field | Should give warning message | Accepting the given data. | dsfggbhds$$ | 1. Go to https://www.pchouse.com.bd/index.php?route=account/register | https://drive.google.com/file/d/18635BDrZY0HSzg0UJayTIHAy5IYSkoLs/view?usp=drive_link |  | Failed
TC_11 |  |  |  | Verify by giving invalid email adresses | Should give warning message | Found as per expectation. | ali@@.com @.com jhkgbjk@ abcd.gmail.com | 1. Go to https://www.pchouse.com.bd/index.php?route=account/register |  |  | Passed
TC_12 |  |  |  | Verify by giving invalid phone number | Should give warning message | Accepting the given data. | ygsdfuygdsauyig | 1. Go to https://www.pchouse.com.bd/index.php?route=account/register | https://drive.google.com/file/d/18635BDrZY0HSzg0UJayTIHAy5IYSkoLs/view?usp=drive_link |  | Failed
TC_13 |  |  |  | Password and Confirm Password fields should be shown in asterisks(*) | Should show asterisk(*) for each character. | Found as per expectation. | password#123 | 1. Go to https://www.pchouse.com.bd/index.php?route=account/register |  |  | Passed
TC_14 |  |  |  | Verify whether the validation is added for the password and confirm whether passwords are the same or not. | Should have validator | Found as per expectation. | password#123 | 1. Go to https://www.pchouse.com.bd/index.php?route=account/register |  |  | Passed
TC_15 |  |  |  | Verify wether an eye icon added to the password field to show original letters if user wants | Should be present | Not found as per expectation | none | 1. Go to https://www.pchouse.com.bd/index.php?route=account/register | https://drive.google.com/file/d/1F_LxfRPl7sGryw8pjEXmFBRdSmJfc7fG/view?usp=drive_link |  | Failed
TC_16 |  |  |  | Send otp to confirm mobile number | Should send otp | Not found as per expectation | none | 1. Go to https://www.pchouse.com.bd/index.php?route=account/register |  |  | Failed
TC_17 |  |  |  | Verify captcha is added to the form or not. | Should have capcha for security | Not found as per expectation | none | 1. Go to https://www.pchouse.com.bd/index.php?route=account/register |  |  | Failed
TC_18 |  |  |  | Verify example or dummy data shown as placeholder text in the fields | Should have placeholder | Found as per expectation | none | 1. Go to https://www.pchouse.com.bd/index.php?route=account/register |  |  | Passed
TC_19 |  |  |  | Verify users can register successfully by entering valid credentials | user should be able to register | Found as per expectation | none | 1. Go to https://www.pchouse.com.bd/index.php?route=account/register |  |  | Passed
TC_20 |  |  |  | Verify that the user is not allowed to register an account with the same registered email by adding plus. | Should give warning message | Not found as per expectation | +xejin74887@konican.com | 1. Go to https://www.pchouse.com.bd/index.php?route=account/register | https://drive.google.com/file/d/1IkfcppwDScgSad4XSjqdxAyfM0phP510/view?usp=drive_link |  | Failed
TC_21 |  |  |  | Verify the email verification link was sent to the user's email address successfully. | Should send vrification mail | Not found as per expectation | none | 1. Go to https://www.pchouse.com.bd/index.php?route=account/register |  |  | Failed
TC_22 |  |  |  | Verify the user is informed to check the spam folder if no email link is found in the inbox. | Should be informed | Not found as per expectation | none | 1. Go to https://www.pchouse.com.bd/index.php?route=account/register |  |  | Failed
TC_23 |  |  |  | Verify Resend Link option is present if the user did not receive the link in the email. | Should have the option | Not found as per expectation | none | 1. Go to https://www.pchouse.com.bd/index.php?route=account/register |  |  | Failed
TC_24 |  |  |  | Verify privacy policy is checked | Should give warning message | Found as per expectation | none | 1. Go to https://www.pchouse.com.bd/index.php?route=account/register |  |  | Passed
TC_25 | Login |  |  | Verify that the user will be able to log in with their account with the correct credential. | Should be able to log in | Found as per expectation | none | 1.Go to https://www.pchouse.com.bd/index.php?route=account/login |  |  | Passed
TC_26 |  |  |  | Verify that the user can log in by entering valid credentials and pressing Enter key. | Should be able to log in | Found as per expectation | none | 1.Go to https://www.pchouse.com.bd/index.php?route=account/login |  |  | Passed
TC_27 |  |  |  | Verify that the user can log in by entering valid credentials and clicking on the login button | Should be able to log in | Found as per expectation | none | 1.Go to https://www.pchouse.com.bd/index.php?route=account/login |  |  | Passed
TC_28 |  |  |  | Verify that the password entered Should be in encrypted form. | Should be encrypted | Found as per expectation | none | 1.Go to https://www.pchouse.com.bd/index.php?route=account/login |  |  | Passed
TC_29 |  |  |  | Verify whether an eye icon is added to the password field or not. | Should be present | Not found as per expectation | none | 1.Go to https://www.pchouse.com.bd/index.php?route=account/login | https://drive.google.com/file/d/1MfhLk-pDI2sGJBJMrqUm2EOK6FFLK1SD/view?usp=drive_link |  | Failed
TC_30 |  |  |  | Verify whether email verification check is available | Should be present | Found as per expectation | none | 1.Go to https://www.pchouse.com.bd/index.php?route=account/login |  |  | Passed
TC_31 |  |  |  | Any captcha on the login form to prevent the robot attack | Should be present | Not found as per expectation | none | 1.Go to https://www.pchouse.com.bd/index.php?route=account/login |  |  | Failed
TC_32 |  |  |  | Verify the error message Should display after just entering an email address and leaving the password field blank and vice versa | Should show error message | Found as per expectation | none | 1.Go to https://www.pchouse.com.bd/index.php?route=account/login |  |  | Passed
TC_33 |  |  |  | Verify the error message Should display after entering the invalid credentials | Should show error message | Found as per expectation | none | 1.Go to https://www.pchouse.com.bd/index.php?route=account/login |  |  | Passed
TC_34 |  |  |  | Check logged in user Should not log out on closing the browser. | Should not log out | Not found as per expectation | none | 1.Go to https://www.pchouse.com.bd/index.php?route=account/login |  |  | Failed
TC_35 |  |  |  | Verify logged-in user doesn’t log out by clicking the back button on the browsers tab. | Should not log out | Found as per expectation | none | 1.Go to https://www.pchouse.com.bd/index.php?route=account/login |  |  | Passed
TC_36 |  |  |  | Verify if logged-in user copies the URL and pastes it into a new browser window, it Should redirect to the login page | Should redirect | Found as per expectation | none | 1.Go to https://www.pchouse.com.bd/index.php?route=account/account |  |  | Passed
TC_37 |  |  |  | Verify it Should not be always in loading in case the user adds an invalid email and password. | Should load | Found as per expectation | none | 1.Go to https://www.pchouse.com.bd/index.php?route=account/login |  |  | Passed
TC_38 |  |  |  | Verify all the functionalities Should be working condition as the user sign-in from social login i-e Facebook and google. | Should be able to log in | Not found as per expectation | none | 1.Go to https://www.pchouse.com.bd/index.php?route=account/login |  |  | Failed
TC_39 |  |  |  | Prevent login page from SQL injection attack | Should not be able to log in | Found as per expectation | ="or' and '="or' | 1.Go to https://www.pchouse.com.bd/index.php?route=account/login |  |  | Passed
TC_40 | Logout |  |  | Verifying if user can log out | Should be able to log out | Not found as per expectation | none | N/A |  |  | Failed
TC_41 | Forgotten password |  |  | Verify that forget password link Should be present on the login screen | Should be present | Found as per expectation | none | 1.Go to https://www.pchouse.com.bd/index.php?route=account/login |  |  | Passed
TC_42 |  |  |  | Verify that on clicking on the forget password link forget password page Should open | Should open | Found as per expectation | none | 1.Go to https://www.pchouse.com.bd/index.php?route=account/login |  |  | Passed
TC_43 |  |  |  | Verify as the user update password, the user Should log out from all browser and devices | Should be logged out | Not found as per expectation | none | 1.Go to https://www.pchouse.com.bd/index.php?route=account/login 2. click on forgottrn password |  |  | Failed
TC_44 |  |  |  | Verify that an email validation is added to the email field. | Should be added | Found as per expectation | none | 1.Go to https://www.pchouse.com.bd/index.php?route=account/login 2. click on forgottrn password |  |  | Passed
TC_45 |  |  |  | Verify the whole button Should be clickable not only the button text. | Should be clickable | Found as per expectation | none | 1.Go to https://www.pchouse.com.bd/index.php?route=account/login 2. click on forgottrn password |  |  | Passed
TC_46 |  |  |  | Verify that the link sent to the user Should expire after a certain time. | Should expire | Not found as per expectation | none | 1.Go to https://www.pchouse.com.bd/index.php?route=account/login 2. click on forgottrn password |  |  | Failed
TC_47 |  |  |  | Verify the error message Should be displayed after entering an unregistered user email id. | Should give error message | Found as per expectation | none | 1.Go to https://www.pchouse.com.bd/index.php?route=account/login 2. click on forgottrn password |  |  | Passed
TC_48 |  |  |  | Verify the confirmation message check your email to recover the password Should be displayed after clicking on the button by entering the registered email id. | Should be displayed | Found as per expectation | none | 1.Go to https://www.pchouse.com.bd/index.php?route=account/login 2. click on forgottrn password |  |  | Passed
TC_49 |  |  |  | Verify that the user will get an email after entering a valid email id in forget password. | Should get mail | Found as per expectation | none | 1.Go to https://www.pchouse.com.bd/index.php?route=account/login 2. click on forgottrn password |  |  | Passed
TC_50 |  |  |  | Verify the email which the user gets against forgot password Should be displayed in the inbox, not in the spam folder | Should not be in the spam folder | Not found as per expectation | none | 1.Go to https://www.pchouse.com.bd/index.php?route=account/login 2. click on forgottrn password |  |  | Failed
TC_51 |  |  |  | Verify the error message should be displayed when clicking on the recover button without entering the email id. | Should give error message | Blank Page | none | 1.Go to https://www.pchouse.com.bd/index.php?route=account/login 2. click on forgottrn password | https://drive.google.com/file/d/1_820m3E8LKcjwPJs4TwOXsqWzG2HXRTf/view?usp=drive_link |  | Failed
TC_52 |  |  |  | Verify user Should be login successfully with the new password not by the old password. | Should not be able to log in with older password | Found as per expectation | none | 1.Go to https://www.pchouse.com.bd/index.php?route=account/login 2. click on forgottrn password |  |  | Passed
TC_53 |  |  |  | Verify that giving invalid format of any kind of email gives error message like invalid email | Should give error message | Found as per expectation | email: ### | 1.Go to https://www.pchouse.com.bd/index.php?route=account/login 2. click on forgottrn password |  |  | Passed
TC_54 | Header |  | Design and basic functions | Verify header section ,icons and texts if are aligned. | Should be aligned | Found as per expectation | none | 1.Go to https://www.pchouse.com.bd/ |  |  | Passed
TC_55 |  |  |  | Verify the same header used on whole website pages. | Header should be the same | Found as per expectation | none | 1.Go to https://www.pchouse.com.bd/ |  |  | Passed
TC_56 |  |  |  | Verify header is sticky on the whole page or fixed as per requirements and design | Should not be sticky | Found as per expectation | none | 1.Go to https://www.pchouse.com.bd/ |  |  | Passed
TC_57 |  |  |  | Verify the home page Should be open on clicking on the logo on all pages. | Should open the home page | Found as per expectation | none | 1.Go to https://www.pchouse.com.bd/ |  |  | Passed
TC_58 |  |  |  | Verify on the mouse hover color changes | Should change color | Found as per expectation | none | 1.Go to https://www.pchouse.com.bd/ |  |  | Passed
TC_59 |  |  |  | Verify search bar is added to the header menu or not | Should be added | Found as per expectation | none | 1.Go to https://www.pchouse.com.bd/ |  |  | Passed
TC_60 |  |  |  | Verify header and body section Should not look the same. | Should be different | Found as per expectation | none | 1.Go to https://www.pchouse.com.bd/ |  |  | Passed
TC_61 |  |  |  | Verify dropdown options added on header shown on mouse hover or click. | Should be added | Found as per expectation | none | 1.Go to https://www.pchouse.com.bd/ |  |  | Passed
TC_62 | Search |  |  | Verify the search field is present and aligned. | Should be present and aligned | Found as per expectation | none | 1.Go to https://www.pchouse.com.bd/ |  |  | Passed
TC_63 |  |  |  | Verify whether placeholder text is added on search or not | Should be added | Found as per expectation | none | 1.Go to https://www.pchouse.com.bd/ |  |  | Passed
TC_64 |  |  |  | Verify search icon is present on the field. | Should be added | Found as per expectation | none | 1.Go to https://www.pchouse.com.bd/ |  |  | Passed
TC_65 |  |  |  | Verify cursor Should be present on click on the search icon. | Should be present | Found as per expectation | none | 1.Go to https://www.pchouse.com.bd/ |  |  | Passed
TC_66 |  |  |  | Verify search is functional and generating the correct result for correct keywords or not by adding a valid search. | Should work correctly | Found as per expectation | none | 1.Go to https://www.pchouse.com.bd/ |  |  | Passed
TC_67 |  |  |  | Verify the search is working by adding keywords and pressing the Enter key on the keyboard. | Should work correctly | Found as per expectation | none | 1.Go to https://www.pchouse.com.bd/ |  |  | Passed
TC_68 |  |  |  | Verify if the user can paste the keyword with the mouse | Should be able to do | Found as per expectation | none | 1.Go to https://www.pchouse.com.bd/ |  |  | Passed
TC_69 |  |  |  | Verify a warning message Should display for blank input | Should give a warning message | Not found as per expectation | none | 1.Go to https://www.pchouse.com.bd/ | https://drive.google.com/file/d/1qsagzfdblUSJHCrfWmihP03ne9rvtO4s/view?usp=drive_link |  | Failed
TC_70 |  |  |  | Verify searching with large number of text does not show any abnormality | Should not show any | Not found as per expectation | none | 1.Go to https://www.pchouse.com.bd/ | https://drive.google.com/file/d/1RwEejO1Cu2k0LouNIlWRJyCY890jlqr2/view?usp=drive_link |  | Failed
TC_71 | Footer |  | Design and basic functions | Verify the footer section is aligned at the end of the page | Should be aligned | Found as per expectation | none | 1.Go to https://www.pchouse.com.bd/ |  |  | Passed
TC_72 |  |  |  | Verify there Should be no extra white space at the end of the footer on high screen resolutions | Should not have | Found as per expectation | none | 1.Go to https://www.pchouse.com.bd/ |  |  | Passed
TC_73 |  |  |  | Verify footer section Should be the same for all pages | Should be same | Found as per expectation | none | 1.Go to https://www.pchouse.com.bd/ |  |  | Passed
TC_74 |  |  |  | Verify by clicking on the links correct pages Should be loaded | Should load correct page | Found as per expectation | none | 1.Go to https://www.pchouse.com.bd/ |  |  | Passed
TC_75 |  |  |  | Verify by clicking on the links correct pages Should be loaded and working | Should be working | Not found as per expectation | Twitter, Linkdin ,Skype and Google links are not working | 1.Go to https://www.pchouse.com.bd/ |  |  | Passed
TC_76 |  |  |  | Verify whether the copyright section is added to the footer or not | Should be added | Found as per expectation | none | 1.Go to https://www.pchouse.com.bd/ |  |  | Passed
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200
201
202
203
204
205
206
207
208
209
210
211
212
213
214
215
216
217
218
219
220
221
222
223
224
225
226
227
228
229
230
231
232
233
234
235
236
237
238
239
240
241
242
243
244
245
246
247
248
249
250
251
252
253
254
255
256
257
258
259
260
261
262
263
264
265
266
267
268
269
270
271
272
273
274
275
276
277
278
279
280
281
282
283
284
285
286
287
288
289
290
291
292
293
294
295
296
297
298
299
300
301
302
303
304
305
306
307
308
309
310
311
312
313
314
315
316
317
318
319
320
321
322
323
324
325
326
327
328
329
330
331
332
333
334
335
336
337
338
339
340
341
342
343
344
345
346
347
348
349
350
351
352
353
354
355
356
357
358
359
360
361
362
363
364
365
366
367
368
369
370
371
372
373
374
375
376
377
378
379
380
381
382
383
384
385
386
387
388
389
390
391
392
393
394
395
396
397
398
399
400
401
402
403
404
405
406
407
408
409
410
411
412
413
414
415
416
417
418
419
420
421
422
423
424
425
426
427
428
429
430
431
432
433
434
435
436
437
438
439
440
441
442
443
444
445
446
447
448
449
450
451
452
453
454
455
456
457
458
459
460
461
462
463
464
465
466
467
468
469
470
471
472
473
474
475
476
477
478
479
480
481
482
483
484
485
486
487
488
489
490
491
492
493
494
495
496
497
498
499
500

## Test Summary Report
Test Case Report | [6 empty] | Result :
Project Name | Pc House Bd
Module Name | Compatibility, Account, Header, Footer |  |  |  |  | Total No. | Status
Feature Name | Registration, User Login, User Logout, Forgotten password, Search, Design and basic functions.
Test Case Version | 1 |  |  |  |  | 51 | PASS
Written By | Syed Muztaba Ali |  |  |  |  | 25 | FAIL
TEST EXECUTION REPORT | [5 empty] | 0 | Not Executed
[6 empty] | 0 | Out of Scope
Test Case | PASS | FAIL | Not Executed | Out Of Scope | Total TC
| 51 | 25 | 0 | 0 | 76
Grand Total | 51 | 25 | 0 | 0 | 76
| Testing Type in Scope | Description
Yes/ No. Justification (If No): | Functional Testing | This type of testing ignores the internal parts and focuses only on the output to check if it is as per the requirement or not.
Yes/ No. Justification (If No): | Integration Testing | Testing of all integrated modules to verify the combined functionality after integration is termed as Integration Testing.
Yes/ No. Justification (If No): | Negative Testing | Testing having the mindset of “attitude to break” using incorrect data and invalid inputs.
Yes/ No. Justification (If No): | Usability Testing | Test application from user friendliness perspective.
Yes/ No. Justification (If No): | Browser Compatibility Testing | Browser Compatibility Testing is performed for web applications and it ensures that the software can run with the combination of different browser and operating system. This type of testing also validates whether web application runs on all versions of all browsers or not.
Yes/ No. Justification (If No): | Boundary Value Testing | There is an upper and lower boundary for each range and testing is performed on these boundary values.
Yes/ No. Justification (If No): | Risk Based Testing Or Regression Testing | Risk-Based Testing includes testing of highly critical functionality, which has the highest impact on business and in which the probability of failure is very high. Testing an application as a whole for the modification in any module or functionality is termed as Regression Testing.

## Bug Report
Bug Reporting
Bug 01 TC_04
Issue: Registered with invalid first name(example using comma as first name)
Reproducing Steps:
1. Goto the URL https://www.pchouse.com.bd/index.php?route=account/register 2. Fill the first and last name with invalid texts (example using only comma) 3. complete registration
Env: Production.
Module: Registration
Priority: Medium
Severity: Minor
Screenshot: Invalid first name
Expected: Should not allow registration with invalid first and last name.
Responsible QA: Syed Muztaba Ali
Bug Reporting
Bug 02 TC_05
Issue: Allows multiple account using same mobile number
Reproducing Steps:
1. Goto the URL https://www.pchouse.com.bd/index.php?route=account/register 2. Create multiple account with same mobile number 3. complete registration
Env: Production.
Module: Registration
Priority: Medium
Severity: Major
Screenshot: multiple account with same mobile number
Expected: Should not allow registration with previously used mobile numbers
Responsible QA: Syed Muztaba Ali
Bug Reporting
# SL 03
Issue: Allows invalid mobile number
Reproducing Steps:
1. Goto the URL https://www.pchouse.com.bd/index.php?route=account/register 2. Create account with invalid mobile number 3. complete registration
Env: Production.
Module: Registration
Priority: Medium
Severity: Major
Screenshot: account with invalid mobile number
Expected: Should not allow invalid mobile numbers
Responsible QA: Syed Muztaba Ali
Bug Reporting
# SL 04
Issue: Eye icon is not added in password field
Reproducing Steps:
1. Goto the URL https://www.pchouse.com.bd/index.php?route=account/register
Env: Production.
Module: Registration
Priority: Low
Severity: Minor
Screenshot: eye icon missing
Expected: icon should be present
Responsible QA: Syed Muztaba Ali
Bug Reporting
# SL 04
Issue: does not send otp to confirm mobile number
Reproducing Steps:
1. Goto the URL https://www.pchouse.com.bd/index.php?route=account/register
Env: Production.
Module: Registration
Priority: Low
Severity: Major
Expected: Should sent OTP
Responsible QA: Syed Muztaba Ali
Bug Reporting
# SL 04
Issue: captcha is not added
Reproducing Steps:
1. Goto the URL https://www.pchouse.com.bd/index.php?route=account/register
Env: Production.
Module: Registration
Priority: Medium
Severity: Major
Expected: cpacha should be present
Responsible QA: Syed Muztaba Ali
Bug Reporting
# SL 05
Issue:User should not be allowed to register an account with the same registered email by adding plus for example useractual+1@gmail.com.
Reproducing Steps:
1. Goto the URL https://www.pchouse.com.bd/index.php?route=account/register
Env: Production.
Module: Registration
Priority: Low
Severity: Minor
Screenshot: allows emails with + sign added
Expected: should not allow
Responsible QA: Syed Muztaba Ali
Bug Reporting
# SL 06
Issue: Does not send email verification link
Reproducing Steps:
1. Goto the URL https://www.pchouse.com.bd/index.php?route=account/register
Env: Production.
Module: Registration
Priority: Medium
Severity: Minor
Expected: should send
Responsible QA: Syed Muztaba Ali
Bug Reporting
# SL 07
Issue: User should be informed to check the spam folder if no email link is found in the inbox.
Reproducing Steps:
1. Goto the URL https://www.pchouse.com.bd/index.php?route=account/register
Env: Production.
Module: Registration
Priority: Low
Severity: Minor
Expected: should be informed
Responsible QA: Syed Muztaba Ali
Bug Reporting
# SL 08
Issue: Resend Link option is not present
Reproducing Steps:
1. Goto the URL https://www.pchouse.com.bd/index.php?route=account/register
Env: Production.
Module: Registration
Priority: High
Severity: Major
Expected: icon should be present
Responsible QA: Syed Muztaba Ali
Bug Reporting
# SL 09
Issue: Eye icon is not added in password field in user login
Reproducing Steps:
1. Goto the URL https://www.pchouse.com.bd/index.php?route=account/login
Env: Production.
Module: User login
Priority: Low
Severity: Minor
Screenshot: eye icon missing
Expected: icon should be present
Responsible QA: Syed Muztaba Ali
Bug Reporting
# SL 10
Issue: No captcha on the login form to prevent the robot attack
Reproducing Steps:
1. Goto the URL https://www.pchouse.com.bd/index.php?route=account/login
Env: Production.
Module: User login
Priority: Low
Severity: Major
Expected: icon should be present
Responsible QA: Syed Muztaba Ali
Bug Reporting
# SL 11
Issue: Logged in user gets logged out on closing the browser.
Reproducing Steps:
1. Goto the URL https://www.pchouse.com.bd/index.php?route=account/login 2. Close Browser
Env: Production.
Module: User login
Priority: High
Severity: Major
Expected: icon should be present
Responsible QA: Syed Muztaba Ali
Bug Reporting
# SL 12
Issue: Social login i-e Facebook and google is not present
Reproducing Steps:
1. Goto the URL https://www.pchouse.com.bd/index.php?route=account/login
Env: Production.
Module: User login
Priority: Low
Severity: Minor
Expected: icon should be present
Responsible QA: Syed Muztaba Ali
Bug Reporting
# SL 13
Issue: User cant log out
Reproducing Steps:
1. N/A
Env: Production.
Module: Log out
Priority: High
Severity: Minor
Screenshot: eye icon missing
Expected: icon should be present
Responsible QA: Syed Muztaba Ali
Bug Reporting
# SL 14
Issue: When user updates password, the user Should log out from all browser and devices
Reproducing Steps:
1. Goto the URL https://www.pchouse.com.bd/index.php?route=account/login 2. click on forgottrn password
Env: Production.
Module: Forgotten password
Priority: High
Severity: Major
Expected: should get logged out
Responsible QA: Syed Muztaba Ali
Bug Reporting
# SL 15
Issue: Link sent to the user does not expire after a certain time.
Reproducing Steps:
1. Goto the URL https://www.pchouse.com.bd/index.php?route=account/login 2. click on forgottrn password
Env: Production.
Module: Forgotten password
Priority:High
Severity: Major
Expected: should expire
Responsible QA: Syed Muztaba Ali
Bug Reporting
# SL 16
Issue: Email which the user gets against forgot password displayed in the spam folder
Reproducing Steps:
1. Goto the URL https://www.pchouse.com.bd/index.php?route=account/login 2. click on forgottrn password
Env: Production.
Module: Forgotten password
Priority: Low
Severity: Minor
Expected: should appear in inbox
Responsible QA: Syed Muztaba Ali
Bug Reporting
# SL 17
Issue: Crushes when clicking on the recover button without entering the email id.
Reproducing Steps:
1. Goto the URL https://www.pchouse.com.bd/index.php?route=account/login 2. click on forgottrn password
Env: Production.
Module: Forgotten password
Priority: High
Severity: Minor
Expected: should show error message
Responsible QA: Syed Muztaba Ali
Bug Reporting
# SL 18
Issue: No error message displayed for blank input
Reproducing Steps:
1.Go to https://www.pchouse.com.bd/ 2. search
Env: Production.
Module: Search
Priority: Low
Severity: Minor
Screenshot: No error message shown
Expected: should show error message
Responsible QA: Syed Muztaba Ali
Bug Reporting
# SL 19
Issue: Searching with large number of text shows abnormality
Reproducing Steps:
1.Go to https://www.pchouse.com.bd/ 2. search with large number
Env: Production.
Module: Search
Priority: Low
Severity: Minor
Screenshot: abnormal result
Expected: should show error message
Responsible QA: Syed Muztaba Ali

## BugReport
Bug Reporting
Bug 01 TC_04
Issue: Registered with invalid first name(example using comma as first name)
Reproducing Steps:
1. Goto the URL https://www.pchouse.com.bd/index.php?route=account/register 2. Fill the first and last name with invalid texts (example using only comma) 3. complete registration
Env: Production.
Module: Registration
Priority: Medium
Severity: Minor
Screenshot: Invalid first name
Expected: Should not allow registration with invalid first and last name.
Responsible QA: Syed Muztaba Ali
Bug Reporting
Bug 02 TC_05
Issue: Registered with invalid first name(example using comma as first name)
Reproducing Steps:
1. Goto the URL https://www.pchouse.com.bd/index.php?route=account/register 2. Fill the first and last name with invalid texts (example using only comma) 3. complete registration
Env: Production.
Module: Registration
Priority: Medium
Severity: Minor
Screenshot: Invalid first name
Expected: Should not allow registration with invalid first and last name.
Responsible QA: Syed Muztaba Ali
Bug Reporting
Bug 03 TC_06
Issue: Registered with invalid first name(example using comma as first name)
Reproducing Steps:
1. Goto the URL https://www.pchouse.com.bd/index.php?route=account/register 2. Fill the first and last name with invalid texts (example using only comma) 3. complete registration
Env: Production.
Module: Registration
Priority: Medium
Severity: Minor
Screenshot: Invalid first name
Expected: Should not allow registration with invalid first and last name.
Responsible QA: Syed Muztaba Ali
Bug Reporting
Bug 04 TC_07
Issue: Registered with invalid first name(example using comma as first name)
Reproducing Steps:
1. Goto the URL https://www.pchouse.com.bd/index.php?route=account/register 2. Fill the first and last name with invalid texts (example using only comma) 3. complete registration
Env: Production.
Module: Registration
Priority: Medium
Severity: Minor
Screenshot: Invalid first name
Expected: Should not allow registration with invalid first and last name.
Responsible QA: Syed Muztaba Ali
Bug Reporting
Bug 05 TC_08
Issue: Allows multiple account using same mobile number
Reproducing Steps:
1. Goto the URL https://www.pchouse.com.bd/index.php?route=account/register 2. Create multiple account with same mobile number 3. complete registration
Env: Production.
Module: Registration
Priority: Medium
Severity: Major
Screenshot: multiple account with same mobile number
Expected: Should not allow registration with previously used mobile numbers
Responsible QA: Syed Muztaba Ali

## Test Metrics
Test Metrics
#SL | Metrics | Description | Result (%)
1 | Percentage of Test Cases Executed | (No. of Test Cases Executed / Total no. of Test Cases Written) * 100 | (76/76)*100 = 100
2 | Percentage of Test Cases Not Executed | (No. of Test Cases not Executed / Total no. of Test Cases Written) * 100 | (0/76)*100 = 0
3 | Percentage of Test Cases Passed | (No. of Test Cases Passed / Total no. of Test Cases Executed) * 100 | (51/76)*100 = 67%
4 | Percentage of Test Cases Failed | (No. of Test Cases Failed / Total no. of Test Cases Executed) * 100 | (25/76)*100 = 33%
5 | Percentage of Test Cases Blocked | (No. of Test Cases Blocked / Total no. of Test Cases Executed) * 100 | (0/76)*100 = 0
6 | Defect Density | No. of Defects found / Size (No. of Requirements) | N/A
7 | Defect Removal Efficiency (DRE) | (Fixed Defects / (Fixed Defects + Missed Defects)) * 100 | N/A
8 | Defect Leakage | (No. of Defects found in UAT/ No. of Defects found in Testing) * 100 | N/A
9 | Defect Rejection Ratio | (No. of Defects Rejected/ Total no. of Defects Raised) * 100 | N/A
10 | Defect Age | Fixed date - Reported date | N/A
11 | Customer Satisfaction | No. of complaints per Period of Time | N/A